🛒 FreshMart Online Grocery Store ───────────────────────────────── PHASE 3 — PROJECT EXECUTION PLAN FastAPI + Flutter ¦ Group 4IS-S3 Presentation Date: Saturday, May 2, 2026

Team Members — Roles Member; ID; Phase 3 Role. Abdelrahman Mostafa (Matrix); 20220197; Flutter — Customer screens + API integration. Omar Mohamed El-Sayed; 20221109; Flutter — Cart + Checkout screens + API integration. Mohamed Sayed Shebl; 20220290; Flutter — All Admin screens + API integration. Donia Kareem Mohamed; 20221051; FastAPI Backend — endpoints, DB schema, models. Asmaa Yasser Hussien; 20221022; FastAPI Backend — endpoints, DB schema, models. A'laa Ibrahim Hosny; 20221024; Not assigned.

SECTION 1 Phase 3 — Overview & Requirements

## What Phase 3 Requires

| # | Deliverable | Details |
| --- | --- | --- |
| 1 | Full Prototype | All screens with complete clickable user flow — built directly in Flutter (the app IS the prototype). |
| 2 | 2 Fully Implemented Functions | Core features with real logic and backend — not just UI. Full stack: Flutter UI → FastAPI → Database. |

## Selected Functions

| ✅ Function 1 | ✅ Function 2 |
| --- | --- |
| Add to Cart + Checkout | Product Management (Admin) |
| Customer adds products → edits cart → completes order with COD. Full order saved to DB and stock reduced. | Admin adds, edits, and deletes products with live DB sync. Includes name, price, stock, category, image. |

SECTION 2 Technical Architecture

## Tech Stack

| Layer | Technology | Responsibility |
| --- | --- | --- |
| Frontend | Flutter (Dart) | All UI screens, user interactions, HTTP calls to API |
| Backend | FastAPI (Python) | REST API endpoints, business logic, database operations |
| Database | SQLite (dev) | Persistent storage for products, orders, users, cart |

## API Endpoints

Function 1 — Cart & Checkout

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /cart/{user_id} | Fetch current cart contents for user |
| POST | /cart/add | Add a product to cart with quantity |
| PUT | /cart/update | Update item quantity in cart |
| DELETE | /cart/remove/{item_id} | Remove a specific item from cart |
| POST | /orders/checkout | Place order, save to DB, reduce stock |

Function 2 — Product Management

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /products | List all products (Admin view) |
| GET | /products/{id} | Get single product details |
| POST | /products/add | Create a new product in DB |
| PUT | /products/{id} | Update existing product data |
| DELETE | /products/{id} | Delete product with confirmation |

SECTION 3 Team Assignments & Task Dependencies

⚠️ CRITICAL: Flutter team CANNOT connect to the API until Donia + Asmaa finish the backend endpoints. The order of work matters — backend must be built first.

## Who Does What

| Team Member(s) | Role | Assigned Work |
| --- | --- | --- |
| Donia + Asmaa | FastAPI Backend | Full backend — DB schema, SQLAlchemy models, all API endpoints for both functions. Work FIRST so the Flutter team can connect. |
| Matrix (Abdelrahman) | Flutter — Customer UI | Home Screen, Product Detail Screen, Checkout Screen, Order Confirmation + API integration for these screens. |
| Omar | Flutter — Cart UI | Cart Screen, full Cart API integration (add/update/remove/view). Supports Matrix with Checkout connection. |
| Shebl (Mohamed Sayed) | Flutter — Admin UI | All Admin screens — Dashboard, Product List, Add Product, Edit Product, Delete confirmation + Admin API integration. |

## Dependency Chain

| Donia + Asmaa: DB Schema + Models | → | Donia + Asmaa: All API Endpoints Live | → | Flutter team connects |
| --- | --- | --- | --- | --- |

| Matrix + Omar + Shebl: Screens built with mock data | → | API ready → each connects their screens → full end-to-end test |
| --- | --- | --- |

SECTION 4 Day-by-Day Timeline (Apr 23 → May 2)

| Date | Donia + Asmaa (FastAPI Backend) | Matrix + Omar + Shebl (All Flutter) |
| --- | --- | --- |
| Apr 23 (Day 1) | Set up FastAPI project. Create DB schema and SQLAlchemy models: Products, Orders, Order_Items, Cart, Users, Payments. | Matrix: Set up Flutter project structure (screens/, models/, services/). Build Home Screen UI with static product grid. Omar: Build Cart Screen UI (static, hardcoded data). Shebl: Build Admin Product List screen (static). |
| Apr 24 (Day 2) | Build & test Products endpoints: GET /products GET /products/{id} POST /products/add PUT /products/{id} DELETE /products/{id} | Matrix: Build Product Detail Screen (static). Create api_service.dart skeleton. Omar: Build Checkout Screen and Order Confirmation Screen (static). Shebl: Build Add Product form screen and Edit Product screen (static). |
| Apr 25 (Day 3) | Build & test Cart endpoints: GET /cart/{user_id} POST /cart/add PUT /cart/update DELETE /cart/remove/{item_id} ✅ MILESTONE: Share API base URL + Postman collection with Matrix, Omar & Shebl. | Matrix: Build Login/Register screen (UI only). Polish Home Screen layout. Omar: Build Order Tracking screen (UI only). Polish Cart Screen. Shebl: Build Delete confirmation dialog. Build Admin Dashboard screen. ⏳ Waiting for API from Donia + Asmaa. |
| Apr 26 (Day 4) | Build & test Checkout endpoint: POST /orders/checkout — save order to DB — reduce product stock ✅ ALL ENDPOINTS DONE. Full backend ready. | Matrix: Connect Home + Product Detail to GET /products. Display real data from API. Omar: Connect Cart Screen to GET /cart/{user_id}. Display real cart. Shebl: Connect Admin Product List to GET /products. Display real products. |
| Apr 27 (Day 5) | Support Flutter team. Fix any API bugs reported by Matrix, Omar, Shebl. Test all endpoints with real Flutter calls. | Matrix: Connect Checkout Screen to POST /orders/checkout. Test full purchase flow. Omar: Connect Cart add/update/remove: POST /cart/add, PUT /cart/update, DELETE /cart/remove. Cart fully functional. Shebl: Connect Add Product to POST /products/add. Connect Edit to PUT /products/{id}. |
| Apr 28 (Day 6) | Add error handling + response validation. Ensure correct HTTP status codes for all endpoints. Fix any bugs from Flutter integration. | Matrix: Test full customer flow: Home → Product Detail → Cart → Checkout → Confirmation. Fix any issues. Omar: Test cart edge cases: empty cart, max quantity, out-of-stock. Fix and polish. Shebl: Connect Delete to DELETE /products/{id}. Test full Admin CRUD: Add → Edit → Delete → Refresh list. |
| Apr 29 (Day 7) | Final backend review. Check all edge cases: empty cart, duplicate products, invalid IDs, insufficient stock. | Matrix + Omar + Shebl: Complete ALL remaining screens. Build full clickable navigation flow connecting every screen. No dead ends. Matrix: User Profile screen (UI only). Omar: Order Tracking screen polish. Shebl: Admin Dashboard final polish. |
| Apr 30 (Day 8) | Full integration testing with complete Flutter app. Support Matrix, Omar & Shebl. Fix any backend issues found during testing. | Matrix + Omar: End-to-end test: Browse → Add to Cart → Checkout → Confirm. Verify order saved in DB. Shebl: End-to-end test: Admin Login → Add Product → Edit → Delete → Verify in list. All three: Rehearse demo roles — who presents which part. |
| May 1 (Day 9) | Ensure FastAPI server runs cleanly. Prepare to explain backend architecture and DB design during presentation. | Everyone: Full dry-run of the complete demo from start to finish. Time it. Fix any last-minute issues. Prepare a backup (screenshots/video) of every working flow in case of live demo failure. |
| May 2 🎯 DEMO | Donia + Asmaa: Run FastAPI server. Be ready to explain backend, DB schema, and API design. | Matrix: Present customer flow — Home → Product → Cart → Checkout → Confirmation. Omar: Demonstrate Cart interactions live. Shebl: Present Admin flow — Add Product → Edit → Delete. |

SECTION 5 Complete Screens List & Owner

## Customer Screens — Matrix + Omar

| # | Screen | Owner | Type | API |
| --- | --- | --- | --- | --- |
| 1 | Home Screen (Product Grid) | Matrix | API Connected | GET /products |
| 2 | Product Detail | Matrix | API Connected | GET /products/{id} |
| 3 | Cart Screen | Omar | API Connected | GET/POST/PUT/DELETE /cart |
| 4 | Checkout Screen | Matrix | API Connected | POST /orders/checkout |
| 5 | Order Confirmation | Omar | UI Only | From Checkout response |
| 6 | Login / Register | Matrix | UI Only | Excluded by TA |
| 7 | Order Tracking | Omar | UI Only | Static |
| 8 | User Profile / Settings | Matrix | UI Only | No |

## Admin Screens — Shebl

| # | Screen | Owner | Type | API |
| --- | --- | --- | --- | --- |
| 1 | Admin Dashboard | Shebl | UI Only | Summary stats |
| 2 | Product List (Admin View) | Shebl | API Connected | GET /products |
| 3 | Add Product Form | Shebl | API Connected | POST /products/add |
| 4 | Edit Product Form | Shebl | API Connected | PUT /products/{id} |
| 5 | Delete Confirmation Dialog | Shebl | API Connected | DELETE /products/{id} |

SECTION 6 Risks & Contingency Plans

| Risk | Impact | Contingency Plan |
| --- | --- | --- |
| Donia + Asmaa backend delayed — Flutter team blocked | 🔴 HIGH | Matrix, Omar & Shebl build ALL screens with hardcoded mock data first. No API needed to build UI. Connect once backend is ready. |
| Flutter team cannot integrate API correctly | 🟠 MED | Donia + Asmaa share Postman collection + example JSON responses. Each Flutter member tests their endpoint with Postman before coding. |
| App crashes during demo | 🔴 HIGH | Full rehearsal on May 1. Keep screenshots and a short video recording of every working flow as a backup. |
| Backend not reachable from phone during demo | 🟠 MED | Test on local Wi-Fi network first. Donia + Asmaa bring a laptop with FastAPI already running. Use emulator as fallback. |

## Integration Day Rules (Apr 29–30)

- Everyone must have their part working before integration day starts.

- Donia + Asmaa run the FastAPI server locally — Flutter apps point to their machine IP on the same Wi-Fi.

- Test the complete user journey: Customer flow (Matrix + Omar) + Admin flow (Shebl), back to back.

- Any screen not connected to API by Apr 29 stays UI-only for the demo — do NOT delay everything for one screen.

- Rehearse the full demo at least twice on May 1. Time it.

🎯 Key Milestone Summary Apr 25 EOD; Donia + Asmaa: All API endpoints running. Share Postman collection with team.. Apr 27 EOD; Matrix: Customer flow (Home → Checkout) connected to API. Omar: Cart fully functional with API.. Apr 28 EOD; Shebl: Full Admin CRUD (Add/Edit/Delete) working with real API.. Apr 30 EOD; All: Full integration tested end-to-end. App demo-ready. No blockers.. May 2; PRESENTATION DAY — Live demo in lab..